## Summary
Smart Meal Planner — progress
Counts update from the Tasks tab. Change a task's Status there (pick from the list); add new tasks as new rows.
Status | Tasks | Share
Done
In review
In progress
To do
Cancelled
All tasks
Complete (done ÷ tasks not cancelled)
Counts 'In review' as done: finished, awaiting merge.
Area | Done | Open
Design
Docs
Foundation
Grocery data
Grocery list
Offers
Offline
Performance
Planner
Preferences
Quality
Recipes
Release
Settings

## Tasks
ID | Area | Task | Status | Owner | PR | Done on | Notes
T01 | Foundation | Initial SwiftUI app, project name and README | Done | Claude | #1–#8 | 2026-10-05
T02 | Design | Revamp the UI across all screens to match the Figma design | Done | Claude | #9 | 2026-10-09
T03 | Design | Branded launch screen and app screenshots in the README | Done | Claude | #10 | 2026-10-09
T04 | Preferences | Derive the shopping region from the postcode | Done | Claude | #11 | 2026-10-09
T05 | Quality | Fix CI: build the Xcode project | Done | Claude | #12 | 2026-10-13
T06 | Quality | Unit tests for every screen, run in CI | Done | Claude | #13, #14 | 2026-10-13
T07 | Design | App icon | Done | Claude | #14 | 2026-10-13
T08 | Settings | Settings screen: theme and version | Done | Claude | #15 | 2026-10-14
T09 | Quality | UI tests and app icon tests | Done | Claude | #15 | 2026-10-14
T10 | Quality | Record every test run in the test report Google Sheet | Done | Claude | #16 | 2026-10-14
T11 | Release | Merge develop into main (UI revamp, region, tests, CI, test report) | Done | You | #17 | 2026-10-15
T12 | Grocery data | Weekly grocery database: each store fetched on its offer day | Done | Claude | #18 | 2026-10-15 | SQLite + GitHub Actions; app downloads only when the feed changed
T13 | Grocery data | Supabase table editor to view and edit prices | Done | Claude | #18–#20 | 2026-10-15
T14 | Grocery data | Fix Supabase sync rejected as a browser | Done | Claude | #19 | 2026-10-15
T15 | Grocery data | Fill an empty Supabase mirror when no store is due | Done | Claude | #20 | 2026-10-15
T16 | Offers | Product photos in the database and on offers | Done | Claude | #21 | 2026-10-15
T17 | Grocery list | Add-to-list buttons, store filters, editable list tab with totals | Done | Claude | #21 | 2026-10-15
T18 | Preferences | Preferences save on the first submit | Done | Claude | #22 | 2026-10-19
T19 | Planner | No dish more than once a day or twice a week | Done | Claude | #22 | 2026-10-19
T20 | Preferences | Number of people; recipes and groceries scale to it | Done | Claude | #22 | 2026-10-19
T21 | Recipes | Prep, cook and total time instead of the step count | Done | Claude | #22 | 2026-10-19
T22 | Recipes | YouTube links open in the YouTube app, else Safari | Done | Claude | #22 | 2026-10-19
T23 | Offers | Supermarket logos in the store filters | Done | Claude | #22 | 2026-10-19
T24 | Settings | Profile: weekly spending and savings against the budget | Done | Claude | #22 | 2026-10-19
T25 | Preferences | Stores within 2 km of the postcode | Done | Claude | #22 | 2026-10-19
T26 | Settings | Notifications when a supermarket's new offers are in | Done | Claude | #22 | 2026-10-19 | Local notifications on each store's offer day
T27 | Recipes | AI-assisted recipe search for the preferences | Done | Claude | #22, #25 | 2026-10-20 | Spoonacular + Claude Haiku via a Supabase function
T28 | Docs | API docs and Postman security checks | Done | Claude | #22 | 2026-10-19
T29 | Docs | README split into summary, features, design, API and test documents | Done | Claude | #22 | 2026-10-19
T30 | Design | Update the Figma screens | Done | Claude | #22 | 2026-10-19
T31 | Offers | Albert Heijn offers from Open Prices; add AH Bonus deals yourself | Done | Claude | #23 | 2026-10-19
T32 | Grocery data | Fix Dirk/DekaMarkt normal prices (Pepsi −93%) | Done | Claude | #24 | 2026-10-20
T33 | Offers | Product photos for every store (refresh the feed) | Done | Claude |  | 2026-10-20 | Re-fetched Jumbo, Dirk, Hoogvliet
T34 | Performance | Fix lag when switching tabs and themes | Done | Claude | #25 | 2026-10-20 | Launch hang 2.0 s → 0.4 s
T35 | Recipes | Real recipes with sources: Spoonacular original link and real YouTube videos | Done | Claude | #25 | 2026-10-20
T36 | Recipes | Detailed steps; fix recipe page alignment | Done | Claude | #25 | 2026-10-20
T37 | Recipes | No built-in sample recipes; on-device AI fallback with recipe-site links | Done | Claude | #25 | 2026-10-20
T38 | Offline | Offline shows stored data or 'needs internet', never samples | Done | Claude | #25 | 2026-10-20
T39 | Docs | README screenshots updated and every feature explained | Done | Claude | #25 | 2026-10-20
T40 | Design | Filter rows fade at the screen edges | Done | Claude | #25 | 2026-10-20
T41 | Grocery list | Show the + only when the list has items | Done | Claude | #25 | 2026-10-20
T42 | Planner | Keep the week within the budget | In review | Claude |  |  | Done on branch feature/budget-share-brochure; PR to come
T43 | Grocery list | Share the grocery list | In review | Claude |  |  | Done on branch feature/budget-share-brochure; PR to come
T44 | Design | App flow diagram in Figma | Done | Claude |  | 2026-10-22 | Frame 'App flow' in the Figma file
T45 | Design | Screen navigation (prototype) in Figma | Done | Claude |  | 2026-10-22 | Tab bar, meal rows, grocery card, back buttons; starts on the empty plan
T46 | Offers | Store brochures with a page-turn effect | Cancelled | You |  |  | Removed from the executables
T47 | Docs | Progress spreadsheet of executed and pending tasks | Done | Claude |  | 2026-10-22 | This file
T48 | Recipes | Deploy the recipe-search function with the Spoonacular and Anthropic keys | To do | You |  |  | Until then the app has no recipes to plan with; steps in docs/DESIGN.md#recipe-search
T49 | Recipes | Add a YouTube Data API key for real recipe videos | To do | You |  |  | Optional; without it the app links a YouTube search
T50 | Release | Merge develop into main for the next release | To do | You |  |  | main was last updated on 15 Oct
T51 | Planner | Monthly planning | To do | Claude |  |  | From the roadmap in docs/SUMMARY.md
T52 | Grocery list | Per-store price comparison in the grocery list | To do | Claude |  |  | From the roadmap
T53 | Planner | Nutrition charts with Swift Charts | To do | Claude |  |  | From the roadmap